## Gantt
| PROJECT TITLE: [enter title] | [5 empty] | Completed |  |  | Remaining |  |  | Weekend
|  |  | Project start date: |  | 2026-03-26
|  |  | Scroll increment: |  | 0 | April | [29 empty] | May | [30 empty] | June
Project timeline | time axis 2026-03-26 to 2026-06-24
# | Task | Assigned to | Progress | Start | Days | time axis 2026-03-26 to 2026-06-24
1 | Requirements analysis | Kamil Wakuła, Krzysztof Tomczyk, Kacper Łukaszewski, Kacper Saletra | 100% | 2026-03-26 | 21 | bar: 2026-03-26 to 2026-04-15
2 | CI and CD implementation | Krzysztof Tomczyk | 100% | 2026-04-16 | 14 | bar: 2026-04-16 to 2026-04-29
3 | Documentation | Krzysztof Tomczyk, Kacper Łukaszewski | 100% | 2026-04-16 | 63 | bar: 2026-04-16 to 2026-06-17
4 | Testing | Kacper Łukaszewski | 100% | 2026-04-30 | 49 | bar: 2026-04-30 to 2026-06-17
5 | API integration | Kamil Wakuła | 100% | 2026-04-16 | 7 | bar: 2026-04-16 to 2026-04-22
6 | Statistical algorithms | Kacper Saletra | 100% | 2026-04-23 | 7 | bar: 2026-04-23 to 2026-04-29
7 | Visualization | Kamil Wakuła | 100% | 2026-04-30 | 7 | bar: 2026-04-30 to 2026-05-06
8 | Exporting | Kacper Saletra | 100% | 2026-05-07 | 7 | bar: 2026-05-07 to 2026-05-13
9 | CLI implementation | Kacper Saletra | 100% | 2026-05-14 | 7 | bar: 2026-05-14 to 2026-05-20

## About
About this template
Gantt Chart — Instructions: • Enter task name (B), assigned person (C), start date (E), number of days (F) • Column D (Progress) accepts values 0%-100% • Dark blue = completed portion, light blue = remaining • Rows without a start date/days will not show a bar — fill in as needed • Field F4 (Scroll increment) shifts the timeline • Need more tasks? Insert a row and copy formulas from an adjacent row