## Burndown
Day | Story Points Goal | Complete | Goal Velocity | Remaining
1 | 27 | 6 | 27 | 26 | Task | Story Points
2 | 22 | 8 | 22 | 18 | Setup CD | 3
3 | 17 | 8 | 17 | 10 | Setup CI with GitHub Actions | 3
4 | 12 | 5 | 12 | 5 | Implement CSV export | 3
5 | 7 | 5 | 7 | 0 | Implement visualization | 5
6 | 2 | 0 | 2 | 0 | Implement statistical algorithms | 8
7 | 0 | 0 | 0 | 0 | Implement CLI navigation system | 5
[5 empty] | Implement NBP API integration | 5
[5 empty] | Total | 32