## Burndown
Day | Story Points Goal | Complete | Goal Velocity | Remaining
1 | 10 | 3 | 10 | 10 | Task | Story Points
2 | 8 | 0 | 8 | 10 | Add Tests | 5
3 | 8 | 5 | 8 | 5 | Create documentation | 3
4 | 3 | 0 | 3 | 5 | Bug Fixes | 5
5 | 3 | 2 | 3 | 3 | Total | 13
6 | 3 | 3 | 3 | 0
7 | 0 | 0 | 0 | 0